##### Project Charter Model Sample

Here is a sample project charter to get you started. This project charter was created for the corporate employee recognition framework.

# Project Charter

|  |
| --- |
| 1.0 Project Identification |
| **Name** | *Employee Recognition Framework* |
| **Description** | *Design, develop and implement the employee recognition framework* |
| **Sponsor** |  |
| **Project Manager** |  |
| **Project Team Resources** |  | Communications, Policy, Healthy Workplace Advisory group, Attraction & Retention working group |

|  |
| --- |
| 2.0 Business reasons for project |
| * Improve government’s ability to attract and recruit high quality candidates and to compete more effectively (with the private sector and other levels of government for candidates)
* Respond to the level of employee engagement and employee perceptions relayed though the corporate employee surveys.
* An element of the Corporate Human Resource Plan
* Component of a healthy workplace
* Element of the Public Service Commission’s Business Plan for 2006/2007
* Complements and builds upon existing departmental recognition activities
* Complements corporate human resource values
* Element of performance management
 |

|  |
| --- |
| **3.0 Project OBJECTIVES (purpose)** |
| * Overall, to create a workplace culture that includes regular recognition and feedback
* To recognize employees for their high-quality service and commitment to public service
* To reinforce linkages between employee performance and department business goals to achieve corporate goals
* To develop tools, guidelines and support for departments to assist with departmental recognition activities
* To develop and implement corporate recognition activities
 |

| **4.0 Project Scope** |
| --- |
| * To include recognition activities for all government departments
* To address two components of recognition - a corporate component and a department component
* Includes guidelines to govern corporate and department activities
* Does not include mandatory requirements
* Framework, research summary, guidelines and tools to be developed and implemented by March 2007
 |

|  |
| --- |
| **5.0 key Project DELIVERABLES** |
| **Name** | **Description** |
| Framework |  Overall roadmap outlining key components of recognition activities |
| Project charter |  |
| Logic Model | Outlines key activities, outcomes and measures |
| Project backgrounder | A supplement to the project charter outlining definitions and outcomes |
| Research summary | To include general, jurisdictional and corporate research |
| Guidelines | To include general program guidelines and financial guidelines |
| Tools and resources | To include templates, guides, sample surveys, quotes, tips, etc… for use by departments |
| Communication/ Implementation plan | Communication of framework, tools resources to stakeholder groups, communication plan |
| Website | To contain framework, guidelines, general information, tools and resources for use by departments, along with information on current activities/events. |

| **6.0 Milestone dates** |
| --- |
| **Item** | **Major Events / Milestones** | **Dates**  |
| 1. | Develop framework |  |
| 2. | Complete a research summary |  |
| 3. | Develop guidelines (general and financial) |  |
| 4. | Consult with departmental reps (i.e. Health, Tourism), Attraction & Retention Working Group, Healthy Workplace Advisory Group |  |
| 5. | Networking/Information event for all departments |  |
| 6. | Develop department toolkit, templates, resources |  |
| 7. | Implementation and communication to stakeholder groups  |  |
| 8. | Website launch |  |
| 9. | Long Service Awards |  |
| 10. | Premiers Award of Excellence |  |
| 11. | Framework evaluation, consultations, lessons learned |  |
| 12. | Premiers Award of Excellence |  |

|  |
| --- |
| **7.0 key ISSUEs** |
| Severity | **Description** |
|  | Different levels of implementation and buy-in; some departments have programs and others have not. |
|  | Departmental recognition activities are not mandatory |
|  | Buy-in from HR community and managers to take ownership of departmental activities |
|  | Maintain momentum and sustainability of activities |
|  | Timelines around the coordination of guideline development with development of the healthy workplace policy |
|  | Timelines around coordinating the recognition framework implementation with the attraction and retention framework implementation |
|  | Employee and manager perceptions |
|  | Public perceptions |

|  |
| --- |
| **8.0 RISKS** |
| **Severity** | **Description** |
|  | Support and buy-in of framework, guidelines and tools from the HR community |
|  | Support and buy-in of framework, guidelines and tools from managers |
|  | Support and buy-in of framework, guidelines and tools from employees |
|  | Implementation timelines |
|  | Availability of supporting resources (i.e. communication, policy) |
|  | Treasury and Policy Board support of guidelines |

| **9.0 Project’s criteria for success (must be measurable)** |
| --- |
| * Increase awareness and consistent practice of recognition throughout the organization (post-presentation evaluations, employee survey results)
* Enhance Government of Nova Scotia’s preferred employer status (public perception studies)
* Create a healthier and more supportive working environment (employee survey results)
* Improved job satisfaction and employee engagement (employee survey results)
* Improved awareness and linkages between department business plans and individual and team performance (employee survey results)
* Increased participation in corporate recognition activities (attendance, # of nominations received)
* Increased favourable employee perceptions of feeling valued for their contributions. (employee survey results)
* Increased favourable employee perceptions of being recognized for a job well done. (employee survey results)
 |

| **10.0 critical success factors** |
| --- |
| * Buy-in and support from senior leaders, HR community, managers, employees
* Effective communication
* PSC and department collaboration
* Employee input into development and implementation of recognition activities
* Employee awareness of department purpose, priorities, objectives, goals and values
* Recognition efforts need to be: timely; meaningful; fair; inclusive
* Activities are supportive of organizational values
 |

| **11.0 Signoff** |
| --- |
| Project Sponsor: Date:  |