## KUTAHYA_RevVIII_February2009
MUNICIPAL SERVICES PROJECT - KUTAHYA MUNICIPALITY PROCUREMENT PLAN (Eighth Revision / 02 February 2009)
BELEDİYE HİZMETLERİ PROJESİ - KÜTAHYA BELEDİYESİ SATINALMA PLANI (Üçüncü Revizyon / 20 Haziran 2006)
1 | 2 | 2 | 3 | 4 |  | 5 |  |  | 6 | 7 | 8 | 9 | 10 | 11
Ref. No. | Description |  | Type | Contract No. | No. of packages | Estimated Cost (Euro) |  |  | Proc. Method | Review by Bank Prior/Post | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date
Sıra No |  | Tanım | Tür | Sözleşme No.su | Paket Sayısı | Tahimini Bedel (Euro 1000) |  |  | Satınalma Yöntemi | DB tarafından İnceleme Önce/Sonra | İhale Dok. / Teklif İsteme Dok. Hazırlanma Tarihi | Tahmini Teklif Açılış / Teklif Sunma Tarihi | Sözleşme İmza Tarihi | Sözleşme Tamamlanma Tarihi
[6 empty] | Toplam | Banka Finansmanı | Belediye Finansmanı
[6 empty] | Total | BF | NBF
| WORKS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network and Reservoir(s) and Renovation of Customer Connections | Şebeke İnşaatı ve Abone Bağlantılarının Yenilenmesi ve Depoların İnşaatı | Works | KUT-W1 | 1 | 4072832 | 3665548.8 | 407283.2 | NCB | POST | June 2007 | August 2007 | October 2007 | December 2008
2 | Construction of Water Network and Reservoir(s) and Renovation of Customer Connections |  | Works | KUT-W2 | 1 | 528926 | 476033.4 | 52892.6 | NCB | POST | February 2009 | April 2009 | May 2009 | September 2009
| Works Sub-Total | İnşaat İşleri Alt-Toplam |  |  |  | 4601758 | 4141582.2 | 460175.8
| GOODS | MAL ALIMI
1 | Procurement of Chlorination Equipment | Su pompalarının yenilenmesi, Klorlama Ekipmanı ve Kurumsal Yapılanma kapsamında yazılım ve donanım alımı | G | KUT-G1 | 1 | 39960 | 35964 | 3996 | Shopping | POST |  |  | April 2008 | November 2008
2 | Procurement of HDPE Drinking Water Pipes |  | G | KUT-G2 | 1 | 33690 | 30321 | 3369 | Shopping | POST |  |  | August 2008 | November 2008
3 | Procurement of Pumps for Water Supply System |  | G | KUT-G3 | 1 | 80000 | 72000 | 8000 | Shopping | POST |  | February 2009 | March 2009 | June 2009
4 | Procurement of Vacuum Truck |  | G | KUT-G4 | 1 | 200000 | 180000 | 20000 | NCB | POST |  | March 2009 | April 2009 | July 2009
| Goods Sub-Total | Mal Alımı Alt-Toplamı |  |  |  | 353650 | 318285 | 35365
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of Environmental Management Plan | Çevre Yönetim Planı Hazırlanması | C | KUT-C1 | 1 | 6162 | 0 | 6162 | 6: LPM; 10: February 2007; 11: June 2007
2 | CANCELLED | İPTAL EDİLMİŞTİR | C | KUT-C2 | multiple | 0 | 0 | 0 | 6: Individual; 7: POST
3 | Preparation of Bidding Documents and Construction Supervision | İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | KUT-C3 | 1 | 290133 | 290133 | 0 | QCBS | PRIOR | June 2006 | August 2006 | February 2007 | April 2010
4 | CANCELLED | Eğitim | C | KUT-C4 | multiple | 0 | 0 | 0 | bar: 10 to 11
| Consultant Sub-Total | Müşavirlik Alt-Toplam |  |  |  | 296295 | 290133 | 6162
| PHYSICAL AND PRICE CONTINGENCY |  |  |  |  | 0 | 0 | 0
| TOTAL | TOPLAM |  |  |  | 5251703 | 4750000.2 | 501702.8
a) | All ICB contracts for works and goods and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be procured through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
LPM: Local Procurement Method

## KUTAHYA_RevVII_October2008
MUNICIPAL SERVICES PROJECT - KUTAHYA MUNICIPALITY PROCUREMENT PLAN (Seventh Revision / 20 October 2008)
BELEDİYE HİZMETLERİ PROJESİ - KÜTAHYA BELEDİYESİ SATINALMA PLANI (Üçüncü Revizyon / 20 Haziran 2006)
1 | 2 | 2 | 3 | 4 |  | 5 |  |  | 6 | 7 | 8 | 9 | 10 | 11
Ref. No. | Description |  | Type | Contract No. | No. of packages | Estimated Cost (Euro) |  |  | Proc. Method | Review by Bank Prior/Post | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date
Sıra No |  | Tanım | Tür | Sözleşme No.su | Paket Sayısı | Tahimini Bedel (Euro 1000) |  |  | Satınalma Yöntemi | DB tarafından İnceleme Önce/Sonra | İhale Dok. / Teklif İsteme Dok. Hazırlanma Tarihi | Tahmini Teklif Açılış / Teklif Sunma Tarihi | Sözleşme İmza Tarihi | Sözleşme Tamamlanma Tarihi
[6 empty] | Toplam | Banka Finansmanı | Belediye Finansmanı
[6 empty] | Total | BF | NBF
| WORKS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network and Reservoir(s) and Renovation of Customer Connections | Şebeke İnşaatı ve Abone Bağlantılarının Yenilenmesi ve Depoların İnşaatı | Works | KUT-W1 | 1 | 4705938 | 4235344.2 | 470593.8 | NCB | POST | June 2007 | August 2007 | October 2007 | December 2008
| Works Sub-Total | İnşaat İşleri Alt-Toplam |  |  |  | 4705938 | 4235344.2 | 470593.8
| GOODS | MAL ALIMI
1 | Procurement of Chlorination Equipment | Su pompalarının yenilenmesi, Klorlama Ekipmanı ve Kurumsal Yapılanma kapsamında yazılım ve donanım alımı | G | KUT-G1 | 1 | 39960 | 35964 | 3996 | Shopping | POST |  |  | April 2008 | October 2008
2 | Procurement of HDPE Drinking Water Pipes |  | G | KUT-G2 | 1 | 33690 | 30321 | 3369 | Shopping | POST |  |  | August 2008 | October 2008
| Goods Sub-Total | Mal Alımı Alt-Toplamı |  |  |  | 73650 | 66285 | 7365
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of Environmental Management Plan | Çevre Yönetim Planı Hazırlanması | C | KUT-C1 | 1 | 6162 | 0 | 6162 | 6: LPM; 10: February 2007; 11: June 2007
2 | CANCELLED | İPTAL EDİLMİŞTİR | C | KUT-C2 | multiple | 0 | 0 | 0 | 6: Individual; 7: POST
3 | Preparation of Bidding Documents and Construction Supervision | İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | KUT-C3 | 1 | 225823 | 225823 | 0 | QCBS | PRIOR | June 2006 | August 2006 | February 2007 | February 2009
4 | Training | Eğitim | C | KUT-C4 | multiple | 6612 | 6612 | 0 | Other | POST |  |  | September 2007 | February 2009
| Consultant Sub-Total | Müşavirlik Alt-Toplam |  |  |  | 238597 | 232435 | 6162
| PHYSICAL AND PRICE CONTINGENCY |  |  |  |  | 215935.8 | 215935.8 | 0
| TOTAL | TOPLAM |  |  |  | 5234120.8 | 4750000 | 484120.8
a) | All ICB contracts for works and goods and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be procured through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
LPM: Local Procurement Method

## KUTAHYA_RevVI_August2008
MUNICIPAL SERVICES PROJECT - KUTAHYA MUNICIPALITY PROCUREMENT PLAN (Sixth Revision / 14 August 2008)
BELEDİYE HİZMETLERİ PROJESİ - KÜTAHYA BELEDİYESİ SATINALMA PLANI (Üçüncü Revizyon / 20 Haziran 2006)
1 | 2 | 2 | 3 | 4 |  | 5 |  |  | 6 | 7 | 8 | 9 | 10 | 11
Ref. No. | Description |  | Type | Contract No. | No. of packages | Estimated Cost (Euro) |  |  | Proc. Method | Review by Bank Prior/Post | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date
Sıra No |  | Tanım | Tür | Sözleşme No.su | Paket Sayısı | Tahimini Bedel (Euro 1000) |  |  | Satınalma Yöntemi | DB tarafından İnceleme Önce/Sonra | İhale Dok. / Teklif İsteme Dok. Hazırlanma Tarihi | Tahmini Teklif Açılış / Teklif Sunma Tarihi | Sözleşme İmza Tarihi | Sözleşme Tamamlanma Tarihi
[6 empty] | Toplam | Banka Finansmanı | Belediye Finansmanı
[6 empty] | Total | BF | NBF
| WORKS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network and Reservoir(s) and Renovation of Customer Connections | Şebeke İnşaatı ve Abone Bağlantılarının Yenilenmesi ve Depoların İnşaatı | Works | KUT-W1 | 1 | 4705938 | 4235344.2 | 470593.8 | NCB | POST | June 2007 | August 2007 | October 2007 | January 2009
| Works Sub-Total | İnşaat İşleri Alt-Toplam |  |  |  | 4705938 | 4235344.2 | 470593.8
| GOODS | MAL ALIMI
1 | Procurement of Chlorination Equipment | Su pompalarının yenilenmesi, Klorlama Ekipmanı ve Kurumsal Yapılanma kapsamında yazılım ve donanım alımı | G | KUT-G1 | 1 | 39960 | 35964 | 3996 | Shopping | POST |  |  | April 2008 | October 2008
2 | Procurement of HDPE Drinking Water Pipes |  | G | KUT-G2 | 1 | 40040 | 36036 | 4004 | Shopping | POST |  |  | August 2008 | October 2008
| Goods Sub-Total | Mal Alımı Alt-Toplamı |  |  |  | 80000 | 72000 | 8000
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of Environmental Management Plan | Çevre Yönetim Planı Hazırlanması | C | KUT-C1 | 1 | 6162 | 0 | 6162 | 6: LPM; 10: February 2007; 11: June 2007
2 | CANCELLED | İPTAL EDİLMİŞTİR | C | KUT-C2 | multiple | 0 | 0 | 0 | 6: Individual; 7: POST
3 | Preparation of Bidding Documents and Construction Supervision | İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | KUT-C3 | 1 | 239215.5 | 239215.5 | 0 | QCBS | PRIOR | June 2006 | August 2006 | February 2007 | February 2009
4 | Training | Eğitim | C | KUT-C4 | multiple | 6612 | 6612 | 0 | Other | POST |  |  | September 2007 | February 2009
| Consultant Sub-Total | Müşavirlik Alt-Toplam |  |  |  | 251989.5 | 245827.5 | 6162
| PHYSICAL AND PRICE CONTINGENCY |  |  |  |  | 196828.3 | 196828.3 | 0
| TOTAL | TOPLAM |  |  |  | 5234755.8 | 4750000 | 484755.8
a) | All ICB contracts for works and goods and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be procured through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
LPM: Local Procurement Method

## KUTAHYA_RevV_DEC2007
MUNICIPAL SERVICES PROJECT - KUTAHYA MUNICIPALITY PROCUREMENT PLAN (Fifth Revision / 27 December, 2007)
BELEDİYE HİZMETLERİ PROJESİ - KÜTAHYA BELEDİYESİ SATINALMA PLANI (Üçüncü Revizyon / 20 Haziran 2006)
1 | 2 | 2 | 3 | 4 |  | 5 |  |  | 6 | 7 | 8 | 9 | 10 | 11
Ref. No. | Description |  | Type | Contract No. | No. of packages | Estimated Cost (Euro) |  |  | Proc. Method | Review by Bank Prior/Post | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date
Sıra No |  | Tanım | Tür | Sözleşme No.su | Paket Sayısı | Tahimini Bedel (Euro 1000) |  |  | Satınalma Yöntemi | DB tarafından İnceleme Önce/Sonra | İhale Dok. / Teklif İsteme Dok. Hazırlanma Tarihi | Tahmini Teklif Açılış / Teklif Sunma Tarihi | Sözleşme İmza Tarihi | Sözleşme Tamamlanma Tarihi
[6 empty] | Toplam | Banka Finansmanı | Belediye Finansmanı
[6 empty] | Total | BF | NBF
| WORKS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network and Reservoir(s) and Renovation of Customer Connections | Şebeke İnşaatı ve Abone Bağlantılarının Yenilenmesi ve Depoların İnşaatı | Works | KUT-W1 | 1 | 4092153 | 3682937.7 | 409215.3 | NCB | POST | June 2007 | August 2007 | October 2007 | October 2008
| Works Sub-Total | İnşaat İşleri Alt-Toplam |  |  |  | 4092153 | 3682937.7 | 409215.3
| GOODS | MAL ALIMI
1 | Renovation of the Water Pumps, Procurement of Chlorination Equipment and Software and Hardware under Institutional Strengthening | Su pompalarının yenilenmesi, Klorlama Ekipmanı ve Kurumsal Yapılanma kapsamında yazılım ve donanım alımı | G | KUT-G1 | multiple | 80000 | 72000 | 8000 | Shopping | POST |  |  | February 2008 | October 2008
| Goods Sub-Total | Mal Alımı Alt-Toplamı |  |  |  | 80000 | 72000 | 8000
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of Environmental Management Plan | Çevre Yönetim Planı Hazırlanması | C | KUT-C1 | 1 | 6162 | 0 | 6162 | 6: LPM; 10: February 2007; 11: June 2007
2 | CANCELLED | İPTAL EDİLMİŞTİR | C | KUT-C2 | multiple | 0 | 0 | 0 | 6: Individual; 7: POST
3 | Preparation of Bidding Documents and Construction Supervision | İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | KUT-C3 | 1 | 198387.5 | 198387.5 | 0 | QCBS | PRIOR | June 2006 | August 2006 | February 2007 | October 2008
4 | Training | Eğitim | C | KUT-C4 | multiple | 6612 | 6612 | 0 | Other | POST |  |  | September 2007 | September 2008
| Consultant Sub-Total | Müşavirlik Alt-Toplam |  |  |  | 211161.5 | 204999.5 | 6162
| PHYSICAL AND PRICE CONTINGENCY |  |  |  |  | 790063 | 790063 | 0
| TOTAL | TOPLAM |  |  |  | 5173377.5 | 4750000.2 | 429539.3
a) | All ICB contracts for works and goods and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be procured through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
LPM: Local Procurement Method

## KUTAHYA_RevIII
MUNICIPAL SERVICES PROJECT - KUTAHYA MUNICIPALITY PROCUREMENT PLAN (Fourth Revision / July 17, 2007)
BELEDİYE HİZMETLERİ PROJESİ - KÜTAHYA BELEDİYESİ SATINALMA PLANI (Üçüncü Revizyon / 20 Haziran 2006)
1 | 2 | 2 | 3 | 4 |  |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11
Ref. No. | Description |  | Type | Contract No. | No. of packages | Estimated Cost (Euro) |  |  | Proc. Method | Review by Bank Prior/Post | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date
Sıra No |  | Tanım | Tür | Sözleşme No.su | Paket Sayısı | Tahimini Bedel (Euro 1000) |  |  | Satınalma Yöntemi | DB tarafından İnceleme Önce/Sonra | İhale Dok. / Teklif İsteme Dok. Hazırlanma Tarihi | Tahmini Teklif Açılış / Teklif Sunma Tarihi | Sözleşme İmza Tarihi | Sözleşme Tamamlanma Tarihi
[6 empty] | Toplam | Banka Finansmanı | Belediye Finansmanı
[6 empty] | Total | BF | NBF
| WORKS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network and Reservoir(s) and Renovation of Customer Connections | Şebeke İnşaatı ve Abone Bağlantılarının Yenilenmesi ve Depoların İnşaatı | Works | KUT-W1 | 1 | 5000000 | 4500000 | 500000 | NCB | POST | June 2007 | August 2007 | September 2007 | October 2008
| Works Sub-Total | İnşaat İşleri Alt-Toplam |  |  |  | 5000000 | 4500000 | 500000
| GOODS | MAL ALIMI
1 | Renovation of the Water Pumps, Procurement of Chlorination Equipment and Software and Hardware under Institutional Strengthening | Su pompalarının yenilenmesi, Klorlama Ekipmanı ve Kurumsal Yapılanma kapsamında yazılım ve donanım alımı | G | KUT-G1 | multiple | 50000 | 45000 | 5000 | Shopping | POST |  |  | September 2007 | October 2008
| Goods Sub-Total | Mal Alımı Alt-Toplamı |  |  |  | 50000 | 45000 | 5000
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of Environmental Management Plan | Çevre Yönetim Planı Hazırlanması | C | KUT-C1 | 1 | 6162 | 0 | 6162 | 6: LPM; 10: February 2007; 11: June 2007
2 | CANCELLED | İPTAL EDİLMİŞTİR | C | KUT-C2 | multiple | 0 | 0 | 0 | 6: Individual; 7: POST
3 | Preparation of Bidding Documents and Construction Supervision | İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | KUT-C3 | 1 | 198387.5 | 198387.5 | 0 | QCBS | PRIOR | June 2006 | August 2006 | February 2007 | October 2008
4 | Training | Eğitim | C | KUT-C4 | multiple | 6612 | 6612 | 0 | Other | POST |  |  | September 2007 | September 2008
| Consultant Sub-Total | Müşavirlik Alt-Toplam |  |  |  | 211161.5 | 204999.5 | 6162
| TOTAL | TOPLAM |  |  |  | 5261161.5 | 4749999.5 | 517324
a) | All ICB contracts for works and goods and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be procured through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
LPM: Local Procurement Method

## KUTAHYA
MUNICIPAL SERVICES PROJECT - KUTAHYA MUNICIPALITY PROCUREMENT PLAN (Second Revision / May 31, 2006)
BELEDİYE HİZMETLERİ PROJESİ - KÜTAHYA BELEDİYESİ TASLAK SATINALMA PLANI (İkinci Versiyon / 31 Mayıs 2006)
1 | 2 | 2 | 3 | 4 |  |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11
Ref. No. | Description |  | Type | Contract No. | No. Of Packages | Estimated Cost (Euro 1000) |  |  | Proc. Method | Review by Bank Prior/Post | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date
Sıra No |  | Tanım | Tür | Sözleşme No.su | Paket Sayısı | Tahimini Bedel (Euro 1000) |  |  | Satınalma Yöntemi | DB tarafından İnceleme Önce/Sonra | İhale Dok. / Teklif İsteme Dok. Hazırlanma Tarihi | Tahmini Teklif Açılış / Teklif Sunma Tarihi | Sözleşme İmza Tarihi | Sözleşme Tamamlanma Tarihi
[6 empty] | Toplam | Banka Finansmanı | Belediye Finansmanı
[6 empty] | Total | BF | NBF
| KUTAHYA MUNICIPALITY | KÜTAHYA BELEDİYESİ
| WORKS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL)
1 | Renovation of Main Transmission Lines and Construction of Reservoirs | Şebeke İnşaatı ve Abone Bağlantılarının Yenilenmesi ve Depoların İnşaatı | Works | KUT-W1 | 1 | 4777.7778 | 4300 | 477.7778 | NCB | POST | February 2007 | March 2007 | May 2007 | November 2008
2 | Construction of of Network and Renovation of Customer Connections | Şebeke İnşaatı ve Abone Bağlantılarının Yenilenmesi | W-Water | KUT-W2 |  | 4.055 | 3.6495 | 0.4055 | NCB | POST | February 2009 | April 2009 | July 2009 | June 2010
| Works Sub-Total | İnşaat İşleri Alt-Toplam |  |  |  | 4777.7778 | 4300 | 477.7778
MAL ALIMI
1 | Renovation of the Water pumps, Procurement of Chlorination Equipment and Procurement of Software and hardware under Institutional Strengthening | İçmesuyu Pompalarının Yenilenmesi, Klor Ekipmanı Alımı, Kurumsal Yapılanma Kapsamında Yazılım ve Donanım Alımı | G | KUT-G1 | multiple | 111.1111 | 100 | 11.1111 | Shopping | POST |  |  | January 2007 | September 2007
| Goods Sub-Total | Mal Alımı Alt-Toplamı |  |  |  | 111.1111 | 100 | 11.1111
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of EMP | Çevre Yönetim Planı Hazırlanması | C | KUT-C1 | 1 | 20 | 20 | 0 | Individual | POST |  |  | June 2006 | September 2006
2 | Project Implementation Management Consultancy Services | Proje Uygulama Yönetimi Müşavirlik Hizmetleri | C | KUT-C2 | multiple | 50 | 50 | 0 | Individual | POST |  |  | June 2006 | June 2009
3 | Preparation of Final Design, Renovation Program, Bidding Documents, Hydraulic Modelling and Construction Supervision | Uygulama Projeleri, Yenileme Programı, İhale Dokümanlarının Hazırlanması, Hidrolik Model Kurulması ve İnşaat Kontrolluğu | C | KUT-C3 | 1 | 240 | 240 | 0 | QCBS | PRIOR | June 2006 | August 2006 | November 2006 | December 2008
4 | Training | Eğitim | C | KUT-C4 | multiple | 40 | 40 | 0 | CQ | POST |  |  | January 2007 | September 2007
| Consultant Sub-Total | Müşavirlik Alt-Toplam |  |  |  | 350 | 350 | 0
| TOTAL | TOPLAM |  |  |  | 5238.8889 | 4750 | 488.8889
a) | All ICB contracts for works and goods and first NCB works, and goods contracts, first Shopping Contracts and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 4 million each may be awarded through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.